## Sheet1
Milestone | Task | Best | Likely | Worst | total hours(likely) | Date
| Develop and document project plan | 1 | 2 | 2
Submit project plan | [5 empty] | 2019-02-12
| Git repository | 1 | 1 | 1
| UART peripheral setup, ISR, and driver | 2 | 3 | 4
| RTC peripheral setup and driver | 3 | 4 | 6
| example code on the FRDM board | 1 | 1 | 1
| Initial makefile, main() and framework | 2 | 3 | 5
| Basic command line prompt and parse | 1 | 2 | 3
| Help function | 1 | 1 | 2
Command prompt with help |  |  |  |  | 15 | 2019-02-18
| Allocate | 1 | 1 | 2
| Free | 1 | 1 | 2
| Invert | 1 | 1 | 2
| Display | 2 | 2 | 3
| Modify | 1 | 1 | 2
Display and modify |  |  |  |  | 6 | 2019-02-21
| Time stampe generation from RTC | 1 | 2 | 3
| Execution time measurement | 1 | 1 | 2
Timed functions |  |  |  |  | 3 | 2019-02-22
| PRNG algorithm and experiment | 2 | 3 | 4
| Write pattern | 1 | 1 | 2
| Verify pattern | 1 | 1 | 2
Feature complete |  |  |  |  | 5 | 2019-02-25
| non-blocking input from terminal | 2 | 2 | 4
| time function | 1 | 1 | 2
| overall test | 2 | 3 | 4
Port to Linux |  |  |  |  | 6 | 2019-03-01
| Use MakeFile to Generate FRDM Executable | 0(aborted) | 6 | 8
| Compensation for RTC | 0(aborted) | 6 | 8
Optional work |  |  |  |  | 12(optional) | 2019-03-06
| Final report | 3 | 4 | 5
Submit final report |  |  |  |  | 39(51 optional) | 2019-03-08